## Sheet1
Team-7 Software Assurance Team meeting Details
Team Members
Shashank Tankasala
Bhavana Gopisetty
Sai Pradeep Koneti
Lucas Asato
Reshma Babu Chethan
Meeting Date | Time of meeting | Meeting Highlights
Aug-30-2020 |  | Team get together through Zoom
Sep-02-2020 | 07:30 PM to 08:30 PM | Introduction with each other with their background
Individual Roles Assignment
A brief discussion on how to select the GitHub open source projects and what projects to be selected.
Weekly Internal Team meeting schedule has made (Every Wednesday from 07:30 PM to 08:30 PM)
Sep-08-2020 | 06:00 PM- 07:30 PM | Individual preferred GitHub project presentation to the team.
Team Finalized two projects from all projects presented.
Team is gonna have deep discussion on the shortlisted projects and prepare the project proposal in today's scheduled meeting"
Sep-09-2020 | 07:30 PM to 08:30 PM | Team finalized to go with Magento2 software and Discussion on clarifications from Professor
Sep-16-2020 | 07:30 PM to 08:30 PM | Discussion on Feedback of Project Prosal and what are the things to be changed in the Proposal
Discussion on changes required in the Proposal
Brief discussion on the weekend Assignmnet Requirements Engineering
Sep-19-2020 | 11:30 AM to 01:30 PM | Discussion on usecase/misuse case scenarios for the magento 2 software
Sep-19-2020 | 06:30 PM to 07:30 PM | Assigned each case to individuals to come with the diagram of usecase/misusecase scenarios as discussed in the meeting
| 07:30 PM to 09:15 PM | Indetail presentation of the usecase/misuse case scenarios by individual's to the team
Discussion of modification on usecase/misusecase scenarios
2020-09-24 | 06:30 PM to 06:45 PM | Team meeting with professor
2020-09-26 | 01:00 PM to 06:30 PM | Final changes in all usecase/misuse case scenarios of System of interest
Discussion on Security related Configuration and Installation of Magento
Committing Final Changes to the Github repo
Oct-04-2020 | 01:00 PM to 02:30 PM | Individual ideas on Assurance cases to the team
Selection of five Top Claims
Assigning each Assurance case to the individuals
Oct-07-2020 | 07:30 PM to 09:00 PM | Assurance case presentation to the team
Discussion on the modifications required to the cases
2020-10-10 | 10:00 AM to 02:30 PM | Modifications to the Assurance cases as per professor comments from the meeting
Indepth look for each assurance case and checking all requiremnts are satisfired
Individual presentation of Assurance cases to the team
Commiting final changes to the github